## Sheet1
Id | State | Sprint end date | IT | UX | Business | Actual | Comment
1 | BOM | SEPTEMBER | Setup servers/laptop; Start app architecture development (UI/Server); Setup accessibility/QA testing patterns | Get environments set up User Research Planning Baseline 508 testing
1 | EOS | Sprint 0 9/13-9/26 | Servers setup; UX research/development starts. Application Architecture development starts. | Get environments set up https://github.com/18F/dol-whd-14c/issues/238
2 | EOS | Sprint 1 9/27-10/10 | All UX Research tasks identified, All requirements identified, All risks identified. Application Architecture Complete, UX Research & design done... Accessibility/QA testing pattern complete. | Initial User Research https://github.com/18F/dol-whd-14c/issues/256 Baseline documentation for accessibility remediation https://github.com/18F/dol-whd-14c/issues/261 Accessibility Assessment https://github.com/18F/dol-whd-14c/issues/242
| BOM | OCTOBER | Feature development starts (document upload, security, Email notification, PDF, WageData??) Features: • File upload • Bugs | Updates to Prototype Design User Testing: - Registration - Employee Wage Data Remediate Accessibility Issues UX Development: - File upload
1 | EOS | Sprint 2 10/11-10/24 | Servers/laptop setup; Application Architecture Complete, UX Research & design done... Accessibility/QA testing pattern complete. Valid file upload, client side validation https://github.com/18F/dol-whd-14c/issues/197 Valid file upload, Rest API https://github.com/18F/dol-whd-14c/issues/263 Captcha removed https://github.com/18F/dol-whd-14c/issues/161 Client side logging https://github.com/18F/dol-whd-14c/issues/259 Server side logging https://github.com/18F/dol-whd-14c/issues/258 Error API https://github.com/18F/dol-whd-14c/issues/260 Logging API https://github.com/18F/dol-whd-14c/issues/309 Application activity logging https://github.com/18F/dol-whd-14c/issues/188 DOL web standard/UI guidelines https://github.com/18F/dol-whd-14c/issues/208 SMTP relay https://github.com/18F/dol-whd-14c/issues/285 ? https://github.com/18F/dol-whd-14c/issues/286 | Prototype updates (registration & wage data) https://github.com/18F/dol-whd-14c/issues/283 Test plan and testing scripts creation https://github.com/18F/dol-whd-14c/issues/293 Accessibility Remediation - https://github.com/18F/dol-whd-14c/issues/287 - https://github.com/18F/dol-whd-14c/issues/295 - https://github.com/18F/dol-whd-14c/issues/298 - https://github.com/18F/dol-whd-14c/issues/276 Instruction language added - https://github.com/18F/dol-whd-14c/issues/300 - https://github.com/18F/dol-whd-14c/issues/301 - https://github.com/18F/dol-whd-14c/issues/305 508 Chores - https://github.com/18F/dol-whd-14c/issues/306 - https://github.com/18F/dol-whd-14c/issues/307 - https://github.com/18F/dol-whd-14c/issues/282 UX design for file upload validation https://github.com/18F/dol-whd-14c/issues/262 | • Helpdesk Research
3 | EOS | Sprint 3 10/25-11/7 | Clear Application on successfull submission https://github.com/18F/dol-whd-14c/issues/120 Application download, PDF Pdf API: https://github.com/18F/dol-whd-14c/issues/239 (David only) Business Requirements for form data: https://github.com/18F/dol-whd-14c/issues/318 Send email: (David to write email API; UX team: Incremental visual design; Harun: UI) WageData UI Work: Make a decision on Wagedata scope of work & Write stories for Harun to start with sliders, datatables. Development of wage data re-design (#344, #345) | Employee wage data re-design https://github.com/18F/dol-whd-14c/issues/210 (Awaiting acceptance) Registration/log-in flow re-design Accessibility Remediation - https://github.com/18F/dol-whd-14c/issues/296 (Blocked) - https://github.com/18F/dol-whd-14c/issues/294 (In Progress, carrying to next sprint) - https://github.com/18F/dol-whd-14c/issues/299 (Backlog) Instruction language added - https://github.com/18F/dol-whd-14c/issues/302 (in Ready for QA) - https://github.com/18F/dol-whd-14c/issues/303 (in ready to start) | Decsision on registration/log-in flow DONE Decision on application download format - DONE
3 | BOM | NOVEMBER | Feature development continues: - Implement Login workflow - PDF attachment -- email to cert team and download to employer - Security ATO complete (critical Defects). | User Research: Change my password Contacting Helpdesk All application screens finalized UX Development: • Registration/Login • Content and visuals on screens finished and updated per feedback | • Review all screens + updates sent to UX | Notes for grooming 11/15: • #390: Is this just a placeholder? All implementation stories for login workflow are in Ready to Start. • #388 and #166: Are these now dups as well and can they be cleaned up? • Verify that uploading files and virus scanning is complete • User testing behind in week Sprint 4 due to outreach
5 | EOS | Sprint 4 11/8-11/21 | PDF Attachment email Api: Write story (needs to be written, dependency to #166) customer email: https://github.com/18f/dol-whd-14c/issues/166 ***BIZ TODO: Biz update with email language. customer download: https://github.com/18F/dol-whd-14c/issues/167 cert team: https://github.com/18f/dol-whd-14c/issues/168 TODO: update requirements for displaying accessibility disclaimer Features complete (includes PDF, document upload, WageData??, ), OMB clearance ready / Security (major defects) Development of registratation/log-in flow (TODO: Madhu to clean up before IPM) https://github.com/18F/dol-whd-14c/issues/339 (epic) https://github.com/18F/dol-whd-14c/issues/131 https://github.com/18F/dol-whd-14c/issues/203 https://github.com/18F/dol-whd-14c/issues/199 https://github.com/18F/dol-whd-14c/issues/214 Banner • Redo banner design (before input) (#388) Security/ATO stories: Encrypt password in web.config: https://github.com/18F/dol-whd-14c/issues/186 Uploaded files are secured: https://github.com/18F/dol-whd-14c/issues/174 User session inactivity: https://github.com/18F/dol-whd-14c/issues/76 WHD needs to provide requirements • Login workflow (#341). Bug blocking accessibility stories | Accessibility remediation: https://github.com/18F/dol-whd-14c/issues/296 (in progress from previous sprint) https://github.com/18F/dol-whd-14c/issues/299 (moved to next sprint) https://github.com/18F/dol-whd-14c/issues/297 (continued in next sprint) Research: • Registration, continued(#380) • Signature on first page (need to hear from policy first) • QA Testing epics (stakeholder/end users/etc): • Wage Data (#394) #340 epic Visual Design + Implementation: Changing my password • https://github.com/18F/dol-whd-14c/issues/69 • Global helpdesk visuals (#381) • Session timeout (#76) • Instruction language added https://github.com/18F/dol-whd-14c/issues/304 https://github.com/18F/dol-whd-14c/issues/303 • Banner (#81) • Login workflow (#341) | Internal application screen review (Policy/WHD front office/SOL) Help desk details Verify signature needs on first page. Are there issues if the preparer filles out the signature? (add to github)
6 | EOS | Sprint 5 11/22-12/5 | ** Previous sprint *** Login workflow 2FA (Can be added anytime) ** Security stories - https://github.com/18F/dol-whd-14c/issues/203 - https://github.com/18F/dol-whd-14c/issues/205 - https://github.com/18F/dol-whd-14c/issues/174 - https://github.com/18F/dol-whd-14c/issues/81 - https://github.com/18F/dol-whd-14c/issues/76 - https://github.com/18F/dol-whd-14c/issues/77 - https://github.com/18F/dol-whd-14c/issues/79 - https://github.com/18F/dol-whd-14c/issues/85 - https://github.com/18F/dol-whd-14c/issues/78 - https://github.com/18F/dol-whd-14c/issues/80 - https://github.com/18F/dol-whd-14c/issues/84 - https://github.com/18F/dol-whd-14c/issues/186 ** Madhu to add a few security stories + prioritize ** RV/LS: Verify which of these are going to be completed before the 12/13 pause. | • Test plan Accessibility remediation https://github.com/18F/dol-whd-14c/issues/299 (from last sprint) https://github.com/18F/dol-whd-14c/issues/297 (blocked) Help text Helpdesk https://github.com/18F/dol-whd-14c/issues/156 QA Epic testing - File upload | PRA submission to OMB
4 | BOM | DECEMBER | Stabilize, Knowledge Transfer, Final Demo/Deploy in DOL | QA Testing
7 | EOS | Sprint 6 12/6-12/19 | Demo/Validation of acceptance criteria.
8 | EOS | Sprint 7 12/20-1/2 | critical/ATO Defect fixes done. App deployed in DOL Dev.
4 | END OF POP |  | All requirements and acceptance criteria met. App deployed in DOL dev. Knowledge transfer complete. All critical/major defects (ATO, features) are addressed.
Note on D7: I left Madhu's initial notes at the top of this cell - I think some are covered with the listed stories, but not all. I believe the cell now reflects all IT work for Sprint 2.